## 4-Week Plan
CV THREAT INTELLIGENCE · 4-WEEK DELIVERY PLAN
WEEK | FOCUS AREA | APPROACH | DELIVERABLES
Week 1 | Baseline & Data | Evaluate the current pipeline across all threat classes before any new development. Establish measurable numbers to compare against later. | · Public dataset clips per threat class Violence · Theft · Weapons · Loitering · Baseline evaluation report Precision · Recall · False Positive Rate · Gap analysis document What detects reliably vs what needs work
Week 2 | Violence Heuristics | Harden the existing pose-based violence layer. Add person tracking across frames, interaction zone logic, and aggressive motion signatures. | · ByteTrack / SORT integrated Consistent person IDs across frames · Interaction zone logic Two tracked persons in proximity → monitor · Aggressive motion signature Wrist/elbow velocity + acceleration buffer · Temporal confirmation gate Rolling window majority vote on threat state
Week 3 | Theft Detection | Build a person-object state machine for theft detection on top of existing pose and object detections. Context filtering to reduce false positives. | · Object attachment tracking Hand keypoint → object bbox proximity flag · Theft state machine per tracked person IDLE → APPROACH → ACQUIRE → DEPART · Updated eval vs Week 1 baseline
Week 4 | Multi-Camera & Demo | Validate the full pipeline across 2–3 simultaneous RTSP camera streams on one machine. Produce a clean stakeholder demo across all threat contexts. | · Multi-stream process manager One detector instance per RTSP camera · Stress test results GPU/CPU load · Latency · Stability · Unified threat dashboard Live threat states across all streams · Demo script All threat contexts · Multiple cameras · Performance summary document Results · Gaps · Phase 2 recommendations